## ISO Gap Assessment
Reference | Requirement / Control | Theme | Assessment Criteria | Implementation Status | Evidence Available | Gap Identified | Recommended Action | Control Owner | Priority | Target Date | Notes | Readiness Score
4.1 | Understanding the organisation and its context | Clause 4 — Context | Internal and external issues relevant to the ISMS are identified, documented and periodically reviewed. | Partially Implemented | Business strategy; technology roadmap | Context analysis exists informally but is not maintained as documented ISMS information. | Develop and maintain a documented organisational context assessment covering internal and external ISMS issues. | Head of Information Security | Medium | 30/11/2026 | Context should be reviewed following significant organisational or environmental change. | 0.5
4.2 | Understanding the needs and expectations of interested parties | Clause 4 — Context | Relevant interested parties and their information security requirements are identified and maintained. | Partially Implemented | Customer contracts; regulatory register; supplier agreements | Stakeholders are known but there is no consolidated interested-parties register linked to ISMS requirements. | Create an interested-parties register documenting security, legal, regulatory and contractual requirements. | Compliance Manager | Medium | 30/11/2026 | Include customers, employees, regulators, suppliers and shareholders where relevant. | 0.5
4.3 | Determining the scope of the ISMS | Clause 4 — Context | The boundaries and applicability of the ISMS are formally defined and maintained as documented information. | Not Implemented | Organisation chart; network diagrams | No formally approved ISMS scope statement exists. | Define and approve the ISMS scope including business functions, locations, technology, interfaces and dependencies. | Head of Information Security | High | 31/10/2026 | ISMS scope must be established before certification assessment. | 0
4.4 | Information security management system | Clause 4 — Context | An ISMS is established, implemented, maintained and continually improved. | Partially Implemented | Security policies; risk register | Security activities exist but are not fully integrated into a formal ISMS. | Establish an ISMS governance framework defining processes, responsibilities, documentation and continual improvement activities. | CISO | High | 31/12/2026 | Existing security processes can be incorporated into the ISMS. | 0.5
5.1 | Leadership and commitment | Clause 5 — Leadership | Top management demonstrates leadership and commitment to the ISMS. | Partially Implemented | Management meeting minutes; security budget approvals | Management supports security activities but formal evidence of ISMS leadership responsibilities is limited. | Establish documented executive ISMS sponsorship and include information security performance in management reviews. | CEO | High | 31/12/2026 | Leadership evidence should demonstrate active oversight rather than passive approval. | 0.5
5.2 | Information security policy | Clause 5 — Leadership | An appropriate information security policy is established, approved, communicated and available to relevant interested parties. | Implemented | Information Security Policy; approval record; employee portal | No material gap identified. | Maintain annual policy review and retain evidence of approval and communication. | CISO | Low | 31/12/2026 | Current policy is approved and communicated. | 1
5.3 | Organisational roles, responsibilities and authorities | Clause 5 — Leadership | Information security roles and responsibilities are assigned and communicated. | Partially Implemented | Job descriptions; organisation chart | Several security responsibilities are understood operationally but are not formally assigned within the ISMS. | Develop an ISMS RACI and formally assign control and process ownership. | CISO | Medium | 31/12/2026 | Align responsibilities with risk and control ownership. | 0.5
6.1 | Actions to address risks and opportunities | Clause 6 — Planning | Information security risks and opportunities are addressed through defined planning processes. | Partially Implemented | Enterprise risk register; security risk assessments | Risk assessment occurs but the ISO-aligned risk methodology and acceptance criteria are not formally approved. | Document and approve the ISMS risk assessment and risk treatment methodology including risk acceptance criteria. | Risk Manager | High | 30/11/2026 | Methodology should support repeatable risk assessment. | 0.5
6.2 | Information security objectives and planning to achieve them | Clause 6 — Planning | Measurable information security objectives are established and monitored. | Partially Implemented | Security KPI reports | Security metrics exist but are not formally linked to approved ISMS objectives. | Define measurable ISMS objectives, owners, targets, monitoring frequency and reporting arrangements. | CISO | Medium | 31/12/2026 | Objectives should align with business and security priorities. | 0.5
6.3 | Planning of changes | Clause 6 — Planning | Changes to the ISMS are carried out in a planned manner. | Not Implemented | Change management procedure | Technical change management exists but there is no defined process for planning changes to the ISMS itself. | Integrate ISMS changes into governance and change-management processes with impact and resource assessment. | ISMS Manager | Medium | 31/01/2027 | Distinguish ISMS change from routine technical change. | 0
7.1 | Resources | Clause 7 — Support | Resources required to establish, maintain and improve the ISMS are determined and provided. | Implemented | Security budget; staffing plan | No material gap identified. | Continue annual resource planning and retain evidence of management decisions. | CISO | Low | 31/12/2026 | Resource requirements should be reconsidered during management review. | 1
7.2 | Competence | Clause 7 — Support | Personnel performing work affecting information security are competent based on education, training or experience. | Partially Implemented | Training records; job descriptions | Training occurs but competency requirements are not consistently mapped to ISMS responsibilities. | Create an ISMS competency matrix and retain evidence of training and professional development. | HR Manager | Medium | 31/01/2027 | Include specialist security and control-owner roles. | 0.5
7.3 | Awareness | Clause 7 — Support | Personnel are aware of the information security policy, their contribution to the ISMS and consequences of nonconformity. | Implemented | Awareness completion records; phishing simulations | No material gap identified. | Maintain annual awareness programme and role-specific security communications. | Security Awareness Lead | Low | 31/12/2026 | Track completion and effectiveness metrics. | 1
7.4 | Communication | Clause 7 — Support | Internal and external communications relevant to the ISMS are determined. | Partially Implemented | Incident communication plan; internal communications | Communication activities exist but the required audience, timing, responsibility and method are not consolidated. | Develop an ISMS communication matrix covering what, when, with whom and how security matters are communicated. | ISMS Manager | Medium | 31/01/2027 | Include regulatory and customer communications where applicable. | 0.5
7.5 | Documented information | Clause 7 — Support | ISMS documented information is appropriately created, updated and controlled. | Partially Implemented | Policy repository; document templates | Document control is inconsistent across security procedures and evidence repositories. | Implement document-control requirements covering approval, versioning, review, access, retention and disposal. | ISMS Manager | High | 31/12/2026 | Create a central ISMS document register. | 0.5
8.1 | Operational planning and control | Clause 8 — Operation | Processes required to meet information security requirements and implement planned actions are controlled. | Partially Implemented | Operational procedures; change records | Operational security processes exist but evidence of consistent ISMS control monitoring is incomplete. | Define operational control monitoring requirements and retain evidence demonstrating consistent execution. | Head of Information Security | High | 31/01/2027 | Control owners should provide evidence at defined intervals. | 0.5
8.2 | Information security risk assessment | Clause 8 — Operation | Risk assessments are performed at planned intervals and when significant changes occur. | Partially Implemented | Risk register; project risk assessments | Assessments occur but there is no documented assessment schedule or consistent trigger criteria. | Establish an annual risk assessment schedule and defined reassessment triggers. | Risk Manager | High | 31/12/2026 | Include major technology, supplier and business changes. | 0.5
8.3 | Information security risk treatment | Clause 8 — Operation | Risk treatment plans are implemented and retained as documented information. | Partially Implemented | Risk treatment tracker | Treatment actions are tracked but formal risk-owner approval and acceptance evidence is inconsistent. | Require documented treatment approval, residual-risk acceptance and closure evidence. | Risk Manager | High | 31/01/2027 | Ensure treatment decisions are traceable to applicable Annex A controls. | 0.5
9.1 | Monitoring, measurement, analysis and evaluation | Clause 9 — Performance Evaluation | The organisation determines what should be monitored and measured to evaluate ISMS performance. | Partially Implemented | Security KPI dashboard | Technical metrics exist but there is no complete ISMS measurement framework. | Define ISMS KPIs, measurement methods, owners, frequency, targets and reporting requirements. | ISMS Manager | Medium | 31/01/2027 | Include effectiveness measures for key controls. | 0.5
9.2 | Internal audit | Clause 9 — Performance Evaluation | Internal audits are conducted at planned intervals against organisational and ISO requirements. | Not Implemented | None | No formal ISMS internal audit programme has been established. | Develop a risk-based internal audit programme, audit schedule, reporting template and corrective-action process. | Internal Audit Manager | Critical | 28/02/2027 | Internal audit must occur before the certification audit. | 0
9.3 | Management review | Clause 9 — Performance Evaluation | Top management reviews the ISMS at planned intervals. | Not Implemented | None | Formal ISO 27001 management review has not yet occurred. | Establish management-review meetings covering required ISMS inputs, decisions and improvement actions. | CISO | Critical | 28/02/2027 | Retain minutes and evidence of decisions and actions. | 0
10.1 | Continual improvement | Clause 10 — Improvement | The suitability, adequacy and effectiveness of the ISMS are continually improved. | Partially Implemented | Security improvement backlog | Improvement activities occur but are not formally linked to ISMS performance and governance. | Establish an ISMS continual-improvement register linked to audits, incidents, metrics and management reviews. | ISMS Manager | Medium | 28/02/2027 | Improvement opportunities should be tracked through closure. | 0.5
10.2 | Nonconformity and corrective action | Clause 10 — Improvement | Nonconformities are managed through correction, root-cause analysis and corrective action. | Not Implemented | General issue tracker | No formal ISMS nonconformity and corrective-action process exists. | Implement a corrective-action procedure covering containment, root cause, action ownership, effectiveness review and closure. | ISMS Manager | High | 28/02/2027 | Process should support audit findings and control failures. | 0
A.5.1 | Policies for information security | A.5 — Organisational | Information security policies are defined, approved, communicated and reviewed at planned intervals. | Implemented | Information Security Policy; policy approval record | No material gap identified. | Maintain annual review cycle and retain approval evidence. | CISO | Low | 31/12/2026 | Policy framework currently operating. | 1
A.5.2 | Information security roles and responsibilities | A.5 — Organisational | Information security responsibilities are defined and allocated according to organisational needs. | Partially Implemented | Organisation chart; job descriptions | Control ownership is not consistently documented across the ISMS. | Develop an ISMS RACI and assign formal control owners. | CISO | Medium | 31/12/2026 | Align with Clause 5.3 remediation. | 0.5
A.5.7 | Threat intelligence | A.5 — Organisational | Information relating to information security threats is collected and analysed to produce relevant intelligence. | Partially Implemented | Vulnerability alerts; vendor security notifications | Threat information is received from several sources but no formal threat-intelligence process exists. | Define threat-intelligence sources, analysis responsibilities, escalation criteria and integration with risk management. | Security Operations Manager | Medium | 31/01/2027 | Focus on threats relevant to the SaaS and cloud environment. | 0.5
A.5.9 | Inventory of information and other associated assets | A.5 — Organisational | An inventory of information and associated assets is developed and maintained, including ownership. | Partially Implemented | IT asset inventory; CMDB | Hardware assets are recorded but SaaS applications and information assets are inconsistently inventoried. | Expand the asset inventory to include information assets and SaaS services and assign ownership. | IT Operations Manager | High | 31/12/2026 | Asset inventory should support risk assessment and classification. | 0.5
A.5.12 | Classification of information | A.5 — Organisational | Information is classified according to security needs and relevant stakeholder requirements. | Partially Implemented | Data handling policy | Classification levels exist but are not consistently applied across business information. | Implement an organisation-wide classification scheme and provide handling guidance for each classification level. | Data Protection Officer | High | 31/01/2027 | Align classification with access and DLP controls. | 0.5
A.5.15 | Access control | A.5 — Organisational | Rules for physical and logical access to information and associated assets are established and implemented. | Implemented | Access Control Policy; RBAC standards | No material gap identified. | Continue periodic access-control policy review and monitor implementation. | Head of Information Security | Low | 31/12/2026 | Supporting controls assessed separately. | 1
A.5.18 | Access rights | A.5 — Organisational | Access rights are provisioned, reviewed, modified and removed according to access-control requirements. | Partially Implemented | Joiner-mover-leaver records; access reviews | Access reviews are performed inconsistently across SaaS applications. | Establish quarterly access recertification for critical systems and retain review evidence. | IT Operations Manager | High | 31/12/2026 | Prioritise privileged and sensitive-data access. | 0.5
A.5.19 | Information security in supplier relationships | A.5 — Organisational | Processes are defined to manage information security risks associated with suppliers. | Partially Implemented | Supplier questionnaire; procurement procedure | Security due diligence is not consistently risk-tiered according to supplier criticality. | Introduce supplier risk classification and proportionate security due diligence requirements. | Third-Party Risk Manager | High | 31/01/2027 | Critical suppliers should receive enhanced assessment. | 0.5
A.5.20 | Addressing information security within supplier agreements | A.5 — Organisational | Relevant information security requirements are established and agreed with suppliers. | Partially Implemented | Supplier contracts; security clauses | Security clauses vary between contracts and minimum requirements are not standardised. | Develop standard contractual security requirements covering incidents, data protection, access, audit and termination. | Legal & Compliance Manager | High | 28/02/2027 | Apply requirements according to supplier risk. | 0.5
A.5.23 | Information security for use of cloud services | A.5 — Organisational | Processes for acquisition, use, management and exit from cloud services are established. | Partially Implemented | Cloud architecture standards; AWS procedures | Cloud security responsibilities are documented technically but lifecycle governance and exit requirements are incomplete. | Develop a cloud security governance standard covering acquisition, shared responsibility, monitoring and exit. | Cloud Security Lead | High | 31/01/2027 | Include SaaS and infrastructure cloud services. | 0.5
A.5.24 | Information security incident management planning and preparation | A.5 — Organisational | Incident-management processes, roles and responsibilities are established and communicated. | Implemented | Incident Response Plan; escalation contacts | No material gap identified. | Continue annual review and exercise the incident response plan. | Head of Information Security | Low | 31/12/2026 | Evidence of exercises should be retained. | 1
A.5.29 | Information security during disruption | A.5 — Organisational | Information security is maintained at an appropriate level during disruption. | Partially Implemented | Business Continuity Plan; disaster recovery procedures | Security requirements during business disruption are not explicitly defined within continuity plans. | Integrate minimum information-security requirements into business continuity and disaster recovery procedures. | Business Continuity Manager | Medium | 31/01/2027 | Consider emergency access and reduced operating modes. | 0.5
A.5.30 | ICT readiness for business continuity | A.5 — Organisational | ICT readiness is planned, implemented, maintained and tested based on business continuity objectives. | Partially Implemented | Disaster Recovery Plan; backup procedures | Recovery procedures exist but restoration and failover testing is not performed consistently. | Establish scheduled recovery and failover tests and retain results against defined recovery objectives. | Infrastructure Manager | High | 28/02/2027 | Testing should demonstrate recovery capability. | 0.5
A.5.31 | Legal, statutory, regulatory and contractual requirements | A.5 — Organisational | Applicable information security requirements are identified, documented and kept current. | Partially Implemented | Regulatory register; customer contracts | Requirements are tracked across separate teams with no consolidated information-security obligations register. | Create and maintain a central legal, regulatory and contractual requirements register. | Compliance Manager | High | 31/12/2026 | Link applicable obligations to policies and controls. | 0.5
A.5.35 | Independent review of information security | A.5 — Organisational | The organisation's approach to information security is independently reviewed at planned intervals. | Not Implemented | None | No independent ISMS review has been performed. | Establish an independent information-security review programme and document findings and corrective actions. | Internal Audit Manager | Critical | 28/02/2027 | Coordinate with the internal audit programme. | 0
A.6.1 | Screening | A.6 — People | Background verification checks are performed prior to employment where appropriate and legally permitted. | Implemented | HR screening procedure; screening records | No material gap identified. | Maintain screening requirements and periodically review role-based screening criteria. | HR Manager | Low | 31/12/2026 | Apply proportionately according to role and legal requirements. | 1
A.6.3 | Information security awareness, education and training | A.6 — People | Personnel receive appropriate information security awareness, education and training. | Implemented | Training records; phishing simulation reports | No material gap identified. | Continue annual training and targeted role-based awareness. | Security Awareness Lead | Low | 31/12/2026 | Use effectiveness metrics to improve the programme. | 1
A.6.5 | Responsibilities after termination or change of employment | A.6 — People | Information security responsibilities remaining after termination or role change are defined and enforced. | Partially Implemented | HR offboarding checklist; employment contracts | Offboarding exists but confirmation of access removal is not consistently retained. | Require documented confirmation of access revocation and continuing confidentiality obligations. | HR Manager | Medium | 31/12/2026 | Integrate with joiner-mover-leaver controls. | 0.5
A.6.7 | Remote working | A.6 — People | Security measures are implemented to protect information accessed or processed through remote working. | Implemented | Remote Working Policy; VPN; endpoint controls | No material gap identified. | Continue monitoring remote-access controls and review the policy annually. | IT Operations Manager | Low | 31/12/2026 | Device compliance should remain enforced. | 1
A.6.8 | Information security event reporting | A.6 — People | Personnel are provided with mechanisms to report observed or suspected information security events promptly. | Implemented | Incident reporting procedure; service desk | No material gap identified. | Maintain awareness of reporting channels and monitor reporting effectiveness. | Security Operations Manager | Low | 31/12/2026 | Include reporting expectations in awareness training. | 1
A.7.1 | Physical security perimeters | A.7 — Physical | Security perimeters are defined and used to protect areas containing information and associated assets. | Implemented | Office access controls; visitor procedures | No material gap identified. | Continue periodic physical-security reviews. | Facilities Manager | Low | 31/12/2026 | Cloud hosting reduces reliance on internal data-centre facilities. | 1
A.7.2 | Physical entry | A.7 — Physical | Secure areas are protected through appropriate entry controls and access points. | Implemented | Badge access system; visitor log | No material gap identified. | Continue access-log review and promptly revoke obsolete badges. | Facilities Manager | Low | 31/12/2026 | Review physical access periodically. | 1
A.7.4 | Physical security monitoring | A.7 — Physical | Premises are continuously monitored for unauthorised physical access. | Partially Implemented | CCTV; building access logs | CCTV coverage exists but formal review and retention requirements are not documented. | Document CCTV monitoring, review, retention and access requirements. | Facilities Manager | Medium | 31/01/2027 | Ensure privacy requirements are considered. | 0.5
A.7.7 | Clear desk and clear screen | A.7 — Physical | Clear desk and clear screen requirements are defined and appropriately enforced. | Partially Implemented | Employee handbook; screen-lock configuration | Clear-screen controls exist technically but clear-desk expectations are not consistently communicated or monitored. | Formalise clear-desk requirements and reinforce them through awareness communications. | Facilities Manager | Low | 31/01/2027 | Focus on areas where sensitive information may be visible. | 0.5
A.8.2 | Privileged access rights | A.8 — Technological | Allocation and use of privileged access rights are restricted and appropriately managed. | Partially Implemented | MFA; administrator account inventory | Privileged accounts are identified but formal periodic recertification and time-limited access are not consistently implemented. | Implement privileged access management and quarterly privileged-access reviews. | Head of Information Security | Critical | 31/12/2026 | High-impact remediation area. | 0.5
A.8.5 | Secure authentication | A.8 — Technological | Secure authentication technologies and procedures are implemented based on access restrictions. | Partially Implemented | MFA; password standard | MFA is not consistently enforced across all business applications and legacy services. | Enforce MFA across supported services and implement stronger authentication for privileged access. | Identity & Access Manager | High | 31/12/2026 | Prioritise internet-facing and privileged services. | 0.5
A.8.7 | Protection against malware | A.8 — Technological | Protection against malware is implemented and supported by appropriate user awareness. | Implemented | EDR; email filtering; security awareness | No material gap identified. | Continue EDR monitoring, tuning and malware-awareness activities. | Security Operations Manager | Low | 31/12/2026 | Monitor endpoint coverage. | 1
A.8.8 | Management of technical vulnerabilities | A.8 — Technological | Information about technical vulnerabilities is obtained, exposure is evaluated and appropriate measures are taken. | Partially Implemented | Vulnerability scans; patch reports | Vulnerability remediation targets are informal and overdue vulnerabilities are not consistently escalated. | Define risk-based remediation SLAs and escalation requirements for overdue vulnerabilities. | Vulnerability Management Lead | Critical | 31/12/2026 | Prioritise internet-facing and Critical vulnerabilities. | 0.5
A.8.9 | Configuration management | A.8 — Technological | Configurations of hardware, software, services and networks are established, documented and monitored. | Partially Implemented | Cloud configuration standards; endpoint baselines | Configuration baselines exist for some technologies but are not centrally governed or continuously monitored. | Establish approved secure configuration baselines and automated compliance monitoring. | Cloud Security Lead | High | 31/01/2027 | Include cloud and endpoint environments. | 0.5
A.8.13 | Information backup | A.8 — Technological | Backup copies are maintained and regularly tested according to agreed backup requirements. | Partially Implemented | Backup logs; backup procedures | Backups are performed but restoration testing is inconsistent. | Establish quarterly restoration testing and retain evidence of successful recovery. | Infrastructure Manager | High | 31/12/2026 | Align tests with recovery objectives. | 0.5
A.8.15 | Logging | A.8 — Technological | Logs recording activities, exceptions, faults and relevant security events are produced, stored, protected and analysed. | Partially Implemented | SIEM; cloud audit logs | Logging exists across critical platforms but retention and monitoring requirements are not consistently defined. | Develop a central logging standard defining required events, retention, protection and monitoring. | Security Operations Manager | High | 31/01/2027 | Include cloud, identity and application logs. | 0.5
A.8.16 | Monitoring activities | A.8 — Technological | Networks, systems and applications are monitored for anomalous behaviour and potential security incidents. | Partially Implemented | SIEM alerts; EDR monitoring | Monitoring coverage is strong for endpoints but incomplete across SaaS applications and cloud services. | Expand monitoring coverage and establish documented alert-review and escalation requirements. | Security Operations Manager | High | 31/01/2027 | Prioritise critical cloud and SaaS services. | 0.5
A.8.20 | Networks security | A.8 — Technological | Networks and network devices are secured, managed and controlled to protect information. | Implemented | Firewall standards; network diagrams; security groups | No material gap identified. | Maintain network-security standards and periodic configuration reviews. | Network Security Lead | Low | 31/12/2026 | Review changes through change-management processes. | 1
A.8.24 | Use of cryptography | A.8 — Technological | Rules for the effective use of cryptography and key management are defined and implemented. | Partially Implemented | Encryption standards; cloud KMS | Cryptography is widely implemented but key-management responsibilities and lifecycle requirements are not consolidated. | Develop a cryptographic standard covering approved algorithms, key ownership, storage, rotation and retirement. | Cloud Security Lead | Medium | 31/01/2027 | Include cloud-managed encryption keys. | 0.5
A.8.25 | Secure development life cycle | A.8 — Technological | Rules for secure development of software and systems are established and applied. | Partially Implemented | SDLC procedure; code review process | Security activities occur during development but security gates are not consistently defined across the lifecycle. | Define secure SDLC requirements including security requirements, testing, approval gates and release criteria. | Engineering Manager | High | 28/02/2027 | Integrate security requirements into development workflows. | 0.5
A.8.28 | Secure coding | A.8 — Technological | Secure coding principles are applied to software development. | Partially Implemented | Code review guidelines; developer training | Secure coding guidance exists but training and compliance evidence are inconsistent. | Establish formal secure-coding standards, annual developer training and compliance checks. | Application Security Lead | Medium | 28/02/2027 | Align with common application-security weaknesses. | 0.5

## Remediation Plan
Remediation ID | ISO Reference | Gap / Finding | Remediation Action | Action Owner | Priority | Target Date | Status | Progress % | Evidence Required | Management Notes
REM-001 | 4.3 | No formally approved ISMS scope statement exists. | Define and approve the ISMS scope covering business functions, locations, technologies, interfaces and dependencies. | Head of Information Security | High | 31/10/2026 | In Progress | 60% | Approved ISMS Scope Statement | Scope workshop completed; management approval pending.
REM-002 | 4.4 | Security activities are not fully integrated into a formal ISMS. | Establish an ISMS governance framework defining processes, responsibilities, documentation and continual improvement. | CISO | High | 31/12/2026 | In Progress | 35% | ISMS Governance Framework; governance meeting records | Core governance structure drafted.
REM-003 | 5.1 | Formal evidence of executive ISMS leadership and oversight is limited. | Establish executive ISMS sponsorship and incorporate security performance into management governance. | CEO | High | 31/12/2026 | In Progress | 30% | Executive sponsorship record; meeting minutes | Executive sponsor identified.
REM-004 | 6.1 | ISO-aligned risk methodology and risk acceptance criteria are not formally approved. | Document and approve the ISMS risk assessment and treatment methodology including acceptance criteria. | Risk Manager | High | 30/11/2026 | In Progress | 55% | Approved Risk Assessment Methodology | Draft methodology under review.
REM-005 | 7.5 | Document control is inconsistent across ISMS procedures and evidence. | Implement document-control requirements covering approval, versioning, review, access, retention and disposal. | ISMS Manager | High | 31/12/2026 | In Progress | 40% | Document Control Procedure; ISMS Document Register | Document register being developed.
REM-006 | 8.1 | Evidence of consistent operational ISMS control monitoring is incomplete. | Define control-monitoring requirements and evidence-retention expectations for control owners. | Head of Information Security | High | 31/01/2027 | Not Started | 0% | Control Monitoring Schedule; control evidence | Dependent on completion of control ownership mapping.
REM-007 | 8.2 | No documented risk assessment schedule or consistent reassessment triggers exist. | Establish an annual ISMS risk assessment schedule and defined reassessment triggers. | Risk Manager | High | 31/12/2026 | In Progress | 35% | Risk Assessment Schedule; reassessment criteria | Schedule structure drafted.
REM-008 | 8.3 | Risk treatment approval and residual-risk acceptance evidence is inconsistent. | Implement documented treatment approval, residual-risk acceptance and closure requirements. | Risk Manager | High | 31/01/2027 | In Progress | 25% | Risk acceptance records; treatment approvals | New approval workflow required.
REM-009 | 9.2 | No formal ISMS internal audit programme has been established. | Develop and execute a risk-based ISMS internal audit programme before certification. | Internal Audit Manager | Critical | 28/02/2027 | Not Started | 0% | Internal Audit Programme; audit reports; corrective actions | Critical certification-readiness dependency.
REM-010 | 9.3 | Formal ISO 27001 management review has not yet occurred. | Establish and conduct management review covering required ISMS inputs, decisions and improvement actions. | CISO | Critical | 28/02/2027 | Not Started | 0% | Management Review Agenda; minutes; action log | Must be completed and evidenced before certification audit.
REM-011 | 10.2 | No formal ISMS nonconformity and corrective-action process exists. | Implement a corrective-action process covering root cause, ownership, effectiveness review and closure. | ISMS Manager | High | 28/02/2027 | Not Started | 0% | Corrective Action Procedure; CAPA register | Process required to support audit findings.
REM-012 | A.5.9 | Asset inventory does not consistently include SaaS applications and information assets. | Expand the asset inventory to include information assets and SaaS services and assign ownership. | IT Operations Manager | High | 31/12/2026 | In Progress | 45% | Updated Asset Register; ownership records | SaaS discovery exercise underway.
REM-013 | A.5.12 | Information classification requirements are not consistently applied. | Implement an organisation-wide classification scheme and handling requirements. | Data Protection Officer | High | 31/01/2027 | In Progress | 30% | Classification Standard; handling guidance | Classification levels agreed; rollout pending.
REM-014 | A.5.18 | Access recertification is inconsistent across SaaS applications. | Establish quarterly access recertification for critical systems and retain evidence. | IT Operations Manager | High | 31/12/2026 | In Progress | 50% | Access Review Records; recertification reports | Critical applications identified.
REM-015 | A.5.19 | Supplier security due diligence is not consistently risk-tiered. | Introduce supplier risk classification and proportionate security assessment requirements. | Third-Party Risk Manager | High | 31/01/2027 | In Progress | 35% | Supplier Risk Methodology; assessment records | Supplier tiers being defined.
REM-016 | A.5.23 | Cloud lifecycle governance and exit requirements are incomplete. | Develop a cloud security governance standard covering acquisition, shared responsibility, monitoring and exit. | Cloud Security Lead | High | 31/01/2027 | In Progress | 40% | Cloud Security Standard; cloud service register | Shared-responsibility requirements being documented.
REM-017 | A.5.35 | No independent ISMS review has been performed. | Establish an independent information-security review programme and track corrective actions. | Internal Audit Manager | Critical | 28/02/2027 | Not Started | 0% | Independent Review Report; corrective-action records | Coordinate with the ISMS internal audit programme.
REM-018 | A.8.2 | Privileged access recertification and time-limited access are not consistently implemented. | Implement privileged access management and quarterly privileged-access reviews. | Head of Information Security | Critical | 31/12/2026 | In Progress | 25% | PAM configuration; privileged access review records | PAM solution requirements defined.
REM-019 | A.8.5 | MFA is not consistently enforced across all business applications and legacy services. | Expand MFA coverage and strengthen authentication for privileged and internet-facing services. | Identity & Access Manager | High | 31/12/2026 | In Progress | 60% | MFA coverage report; authentication standard | Legacy applications remain outstanding.
REM-020 | A.8.8 | Vulnerability remediation targets are informal and overdue vulnerabilities are not consistently escalated. | Define risk-based remediation SLAs and escalation requirements for overdue vulnerabilities. | Vulnerability Management Lead | Critical | 31/12/2026 | In Progress | 45% | Vulnerability Management Standard; SLA reports | Draft remediation SLAs prepared.
REM-021 | A.8.9 | Secure configuration baselines are not centrally governed or continuously monitored. | Establish approved secure configuration baselines and automated compliance monitoring. | Cloud Security Lead | High | 31/01/2027 | In Progress | 35% | Secure Configuration Standards; compliance reports | Initial AWS baseline under development.
REM-022 | A.8.13 | Backup restoration testing is inconsistent. | Establish quarterly restoration testing and retain evidence of successful recovery. | Infrastructure Manager | High | 31/12/2026 | In Progress | 50% | Restoration Test Reports; recovery results | Next restoration exercise scheduled.
REM-023 | A.8.15 | Log retention and monitoring requirements are not consistently defined. | Develop a central logging standard defining required events, retention, protection and monitoring. | Security Operations Manager | High | 31/01/2027 | In Progress | 40% | Logging Standard; SIEM configuration evidence | Current log sources being inventoried.
REM-024 | A.8.16 | Monitoring coverage is incomplete across SaaS applications and cloud services. | Expand security monitoring coverage and formalise alert review and escalation requirements. | Security Operations Manager | High | 31/01/2027 | In Progress | 30% | Monitoring Coverage Matrix; alert procedures | Priority SaaS integrations identified.
REM-025 | A.8.25 | Security gates are not consistently defined across the software development lifecycle. | Define secure SDLC requirements including security testing, approval gates and release criteria. | Engineering Manager | High | 28/02/2027 | In Progress | 25% | Secure SDLC Standard; pipeline evidence | Engineering and security workshops underway.

## Evidence Register
Evidence ID | ISO Reference | Evidence / Document | Evidence Type | Document Owner | Review Frequency | Last Reviewed | Next Review | Evidence Status | Storage Location | Notes
EVD-001 | 4.3 | ISMS Scope Statement | Governance Document | Head of Information Security | Annual |  | 31/10/2026 | Required | ISMS / Governance | Currently being developed as part of remediation.
EVD-002 | 4.4 | ISMS Governance Framework | Governance Document | CISO | Annual |  | 31/12/2026 | Required | ISMS / Governance | Formal ISMS governance structure not yet approved.
EVD-003 | 5.2 | Information Security Policy | Policy | CISO | Annual | 15/06/2026 | 15/06/2027 | Available | ISMS / Policies | Approved and communicated to employees.
EVD-004 | 5.3 | ISMS RACI Matrix | Governance Document | CISO | Annual |  | 31/12/2026 | Required | ISMS / Governance | Required to formalise ISMS responsibilities.
EVD-005 | 6.1 | ISMS Risk Assessment Methodology | Risk Document | Risk Manager | Annual |  | 30/11/2026 | In Development | ISMS / Risk Management | Draft methodology currently under review.
EVD-006 | 6.2 | Information Security Objectives & KPI Register | Performance Record | CISO | Quarterly |  | 31/12/2026 | In Development | ISMS / Performance | Security metrics exist but require formal linkage to ISMS objectives.
EVD-007 | 7.2 | ISMS Competency Matrix | HR Record | HR Manager | Annual |  | 31/01/2027 | Required | ISMS / Competence | Competency requirements need mapping to ISMS roles.
EVD-008 | 7.3 | Security Awareness Training Records | Training Record | Security Awareness Lead | Annual | 30/06/2026 | 30/06/2027 | Available | ISMS / Training | Includes completion records and phishing simulations.
EVD-009 | 7.5 | Document Control Procedure | Procedure | ISMS Manager | Annual |  | 31/12/2026 | In Development | ISMS / Document Control | Document approval and version-control requirements being established.
EVD-010 | 8.2 | ISMS Risk Assessment Schedule | Risk Record | Risk Manager | Annual |  | 31/12/2026 | In Development | ISMS / Risk Management | Will define planned and event-driven reassessments.
EVD-011 | 8.3 | Risk Treatment & Acceptance Records | Risk Record | Risk Manager | Quarterly |  | 31/01/2027 | Required | ISMS / Risk Management | Formal approval and acceptance evidence currently inconsistent.
EVD-012 | 9.1 | ISMS KPI Dashboard | Performance Record | ISMS Manager | Monthly | 31/08/2026 | 30/09/2026 | Available | ISMS / Performance | Existing dashboard requires additional ISMS effectiveness metrics.
EVD-013 | 9.2 | Internal Audit Programme | Audit Record | Internal Audit Manager | Annual |  | 28/02/2027 | Required | ISMS / Internal Audit | Formal ISMS audit programme not yet established.
EVD-014 | 9.2 | Internal Audit Report | Audit Record | Internal Audit Manager | Annual |  | 28/02/2027 | Required | ISMS / Internal Audit | To be generated following first internal ISMS audit.
EVD-015 | 9.3 | Management Review Minutes | Management Record | CISO | Annual |  | 28/02/2027 | Required | ISMS / Management Review | First formal ISO 27001 management review pending.
EVD-016 | 10.2 | Corrective Action Register | Improvement Record | ISMS Manager | Monthly |  | 28/02/2027 | Required | ISMS / Improvement | Will record nonconformities, root causes and corrective actions.
EVD-017 | A.5.9 | Asset Register | Operational Record | IT Operations Manager | Quarterly | 30/06/2026 | 30/09/2026 | Partial | ISMS / Asset Management | SaaS and information assets require additional coverage.
EVD-018 | A.5.12 | Information Classification Standard | Standard | Data Protection Officer | Annual |  | 31/01/2027 | In Development | ISMS / Data Protection | Classification levels agreed; implementation pending.
EVD-019 | A.5.18 | Access Recertification Records | Access Record | IT Operations Manager | Quarterly |  | 31/12/2026 | Partial | ISMS / Access Control | Review evidence inconsistent across SaaS applications.
EVD-020 | A.5.19 | Supplier Security Assessment Records | Third-Party Record | Third-Party Risk Manager | Annual |  | 31/01/2027 | Partial | ISMS / Third-Party Risk | Current assessments are not consistently risk-tiered.
EVD-021 | A.5.23 | Cloud Security Governance Standard | Standard | Cloud Security Lead | Annual |  | 31/01/2027 | In Development | ISMS / Cloud Security | Lifecycle and exit requirements being added.
EVD-022 | A.5.24 | Incident Response Plan | Procedure | Head of Information Security | Annual | 20/05/2026 | 20/05/2027 | Available | ISMS / Incident Management | Approved incident response process currently in operation.
EVD-023 | A.5.30 | Disaster Recovery Test Report | Test Record | Infrastructure Manager | Annual |  | 28/02/2027 | Required | ISMS / Business Continuity | Formal recovery testing evidence required.
EVD-024 | A.5.35 | Independent Information Security Review | Audit Record | Internal Audit Manager | Annual |  | 28/02/2027 | Required | ISMS / Internal Audit | No independent ISMS review completed yet.
EVD-025 | A.6.1 | Employee Screening Records | HR Record | HR Manager | On Hire | 2026-01-09 |  | Available | ISMS / HR Security | Screening evidence maintained by HR.
EVD-026 | A.6.3 | Security Awareness & Phishing Reports | Training Record | Security Awareness Lead | Quarterly | 30/06/2026 | 30/09/2026 | Available | ISMS / Training | Used to measure awareness effectiveness.
EVD-027 | A.7.2 | Physical Access Records | Physical Security Record | Facilities Manager | Quarterly | 30/06/2026 | 30/09/2026 | Available | ISMS / Physical Security | Badge and visitor access records retained.
EVD-028 | A.8.2 | Privileged Access Review Records | Access Record | Head of Information Security | Quarterly |  | 31/12/2026 | Partial | ISMS / Access Control | Quarterly recertification not yet consistently performed.
EVD-029 | A.8.5 | MFA Coverage Report | Technical Evidence | Identity & Access Manager | Monthly | 31/08/2026 | 30/09/2026 | Partial | ISMS / Identity Security | Legacy applications remain outside full MFA coverage.
EVD-030 | A.8.7 | EDR Coverage Report | Technical Evidence | Security Operations Manager | Monthly | 31/08/2026 | 30/09/2026 | Available | ISMS / Security Operations | Endpoint protection coverage monitored centrally.
EVD-031 | A.8.8 | Vulnerability Management Reports | Technical Evidence | Vulnerability Management Lead | Monthly | 31/08/2026 | 30/09/2026 | Partial | ISMS / Vulnerability Management | Remediation SLAs and overdue escalation require formalisation.
EVD-032 | A.8.9 | Secure Configuration Baselines | Standard | Cloud Security Lead | Annual |  | 31/01/2027 | In Development | ISMS / Configuration Management | Baselines under development for cloud and endpoint environments.
EVD-033 | A.8.13 | Backup & Restoration Test Records | Test Record | Infrastructure Manager | Quarterly |  | 31/12/2026 | Partial | ISMS / Business Continuity | Backups exist but restoration evidence is inconsistent.
EVD-034 | A.8.15 | Central Logging Standard | Standard | Security Operations Manager | Annual |  | 31/01/2027 | In Development | ISMS / Security Operations | Log retention and monitoring requirements being consolidated.
EVD-035 | A.8.16 | Security Monitoring Coverage Matrix | Technical Evidence | Security Operations Manager | Quarterly |  | 31/01/2027 | In Development | ISMS / Security Operations | SaaS and cloud monitoring coverage requires expansion.
EVD-036 | A.8.25 | Secure SDLC Standard | Standard | Engineering Manager | Annual |  | 28/02/2027 | In Development | ISMS / Secure Development | Security gates and release criteria being formalised.

## SoA
Control Reference | Annex A Control | Applicable? | Justification for Inclusion / Exclusion | Implementation Status | Supporting Evidence | Control Owner | Remediation Reference | Review Notes
A.5.1 | Policies for information security | Yes | Required to establish management direction and organisational expectations for information security. | Implemented | Information Security Policy | CISO |  | Policy approved and communicated.
A.5.2 | Information security roles and responsibilities | Yes | Required to establish accountability for information security responsibilities and ISMS controls. | Partially Implemented | Organisation Chart; Job Descriptions | CISO |  | Formal ISMS RACI remains required.
A.5.7 | Threat intelligence | Yes | CloudCore requires relevant threat information to support security monitoring and risk management. | Partially Implemented | Vulnerability Alerts; Vendor Security Notifications | Security Operations Manager |  | Formal threat-intelligence process requires development.
A.5.9 | Inventory of information and other associated assets | Yes | Required to identify and manage information, technology and SaaS assets supporting CloudCore services. | Partially Implemented | Asset Register | IT Operations Manager | REM-012 | SaaS and information asset coverage requires improvement.
A.5.12 | Classification of information | Yes | Required to ensure information receives protection appropriate to its sensitivity and business value. | Partially Implemented | Data Handling Policy | Data Protection Officer | REM-013 | Classification scheme requires consistent implementation.
A.5.15 | Access control | Yes | Required to restrict access to CloudCore systems, services and information according to business and security requirements. | Implemented | Access Control Policy; RBAC Standards | Head of Information Security |  | Control operating.
A.5.18 | Access rights | Yes | Required to govern provisioning, review, modification and removal of user access rights. | Partially Implemented | Access Review Records | IT Operations Manager | REM-014 | Quarterly recertification required for critical applications.
A.5.19 | Information security in supplier relationships | Yes | CloudCore relies on third-party SaaS and technology suppliers that may introduce information security risk. | Partially Implemented | Supplier Security Assessments | Third-Party Risk Manager | REM-015 | Risk-tiered supplier assessment required.
A.5.20 | Addressing information security within supplier agreements | Yes | Supplier contracts require appropriate security obligations to protect CloudCore information and services. | Partially Implemented | Supplier Contracts; Security Clauses | Legal & Compliance Manager |  | Minimum contractual security requirements require standardisation.
A.5.23 | Information security for use of cloud services | Yes | Cloud services are fundamental to CloudCore's SaaS operating model and require lifecycle security governance. | Partially Implemented | Cloud Architecture Standards | Cloud Security Lead | REM-016 | Cloud lifecycle and exit governance requires improvement.
A.5.24 | Information security incident management planning and preparation | Yes | Required to ensure CloudCore can respond consistently to information security incidents. | Implemented | Incident Response Plan | Head of Information Security |  | Incident response process established.
A.5.29 | Information security during disruption | Yes | Required to maintain appropriate information security controls during business or technology disruption. | Partially Implemented | Business Continuity Plan | Business Continuity Manager |  | Security requirements during disruption require greater definition.
A.5.30 | ICT readiness for business continuity | Yes | CloudCore's SaaS services require tested technology recovery capability to support continuity objectives. | Partially Implemented | Disaster Recovery Plan | Infrastructure Manager |  | Recovery and failover testing requires improvement.
A.5.31 | Legal, statutory, regulatory and contractual requirements | Yes | CloudCore must identify and comply with applicable legal, regulatory and contractual information security obligations. | Partially Implemented | Regulatory Register; Customer Contracts | Compliance Manager |  | Consolidated information-security obligations register required.
A.5.35 | Independent review of information security | Yes | Independent review is required to evaluate the continuing suitability and effectiveness of CloudCore's information security approach. | Not Implemented | No evidence currently available | Internal Audit Manager | REM-017 | Independent review must be established before certification readiness.
A.6.1 | Screening | Yes | Relevant personnel require proportionate pre-employment screening based on role and legal requirements. | Implemented | Employee Screening Records | HR Manager |  | Control operating.
A.6.3 | Information security awareness, education and training | Yes | Personnel require appropriate awareness and training to understand and fulfil their security responsibilities. | Implemented | Security Awareness & Phishing Reports | Security Awareness Lead |  | Control operating.
A.6.5 | Responsibilities after termination or change of employment | Yes | Security responsibilities and access obligations must remain appropriately managed following employment changes. | Partially Implemented | HR Offboarding Checklist | HR Manager |  | Access-removal evidence requires improvement.
A.6.7 | Remote working | Yes | CloudCore supports remote working and must protect information accessed outside corporate premises. | Implemented | Remote Working Policy; VPN; Endpoint Controls | IT Operations Manager |  | Control operating.
A.6.8 | Information security event reporting | Yes | Personnel need clear mechanisms to report suspected information security events promptly. | Implemented | Incident Reporting Procedure | Security Operations Manager |  | Control operating.
A.7.1 | Physical security perimeters | Yes | CloudCore office areas and information-processing equipment require protection against unauthorised physical access. | Implemented | Office Access Controls; Visitor Procedures | Facilities Manager |  | Control operating.
A.7.2 | Physical entry | Yes | Physical entry to CloudCore premises and secure areas must be appropriately controlled. | Implemented | Badge Access System; Visitor Logs | Facilities Manager |  | Control operating.
A.7.4 | Physical security monitoring | Yes | Monitoring supports detection and investigation of unauthorised access to CloudCore premises. | Partially Implemented | CCTV; Building Access Logs | Facilities Manager |  | CCTV governance and retention requirements require documentation.
A.7.7 | Clear desk and clear screen | Yes | Required to reduce unauthorised exposure of sensitive information in office environments. | Partially Implemented | Employee Handbook; Screen-Lock Configuration | Facilities Manager |  | Clear-desk expectations require stronger communication.
A.8.2 | Privileged access rights | Yes | CloudCore administrators possess elevated access capable of significantly affecting systems and information. | Partially Implemented | Privileged Account Inventory; MFA | Head of Information Security | REM-018 | PAM and quarterly privileged-access review required.
A.8.5 | Secure authentication | Yes | Strong authentication is required for CloudCore applications, cloud services and privileged access. | Partially Implemented | MFA Coverage Report; Password Standard | Identity & Access Manager | REM-019 | MFA coverage requires expansion.
A.8.7 | Protection against malware | Yes | CloudCore endpoints and systems require protection against malicious software. | Implemented | EDR Coverage Report; Email Filtering | Security Operations Manager |  | Control operating.
A.8.8 | Management of technical vulnerabilities | Yes | CloudCore's internet-facing SaaS environment requires timely identification and remediation of technical vulnerabilities. | Partially Implemented | Vulnerability Management Reports | Vulnerability Management Lead | REM-020 | Risk-based remediation SLAs required.
A.8.9 | Configuration management | Yes | Secure and consistent configuration is necessary across CloudCore's cloud and endpoint environments. | Partially Implemented | Cloud Configuration Standards | Cloud Security Lead | REM-021 | Central baselines and automated monitoring required.
A.8.13 | Information backup | Yes | Backups are required to support recovery of CloudCore information and services following disruption. | Partially Implemented | Backup Logs; Backup Procedures | Infrastructure Manager | REM-022 | Restoration testing requires formalisation.
A.8.15 | Logging | Yes | Security and operational logs are required to detect, investigate and evidence relevant activity. | Partially Implemented | SIEM; Cloud Audit Logs | Security Operations Manager | REM-023 | Central logging standard required.
A.8.16 | Monitoring activities | Yes | CloudCore requires security monitoring to identify anomalous activity across critical technology services. | Partially Implemented | SIEM Alerts; EDR Monitoring | Security Operations Manager | REM-024 | Cloud and SaaS monitoring coverage requires expansion.
A.8.20 | Networks security | Yes | Network security controls are required to protect CloudCore systems, services and data flows. | Implemented | Firewall Standards; Network Diagrams | Network Security Lead |  | Control operating.
A.8.24 | Use of cryptography | Yes | CloudCore processes sensitive business and customer information requiring appropriate encryption and key management. | Partially Implemented | Encryption Standards; Cloud KMS | Cloud Security Lead |  | Key-management lifecycle requirements require consolidation.
A.8.25 | Secure development life cycle | Yes | CloudCore develops SaaS software and therefore requires security throughout the development lifecycle. | Partially Implemented | SDLC Procedure; Code Review Process | Engineering Manager | REM-025 | Security gates and release criteria require formalisation.
A.8.28 | Secure coding | Yes | Secure coding practices are required to reduce vulnerabilities introduced during software development. | Partially Implemented | Code Review Guidelines; Developer Training | Application Security Lead |  | Secure-coding standards and compliance evidence require improvement.

## Executive Dashboard
CloudCore Systems Ltd — ISO/IEC 27001:2022 Readiness Assessment
Executive ISMS Readiness Dashboard ¦ September 2026
59 | 14 | 39 | 6 | 56.78%
Assessments Completed | Implemented | Partial | Not Implemented | Readiness
Management Assessment
CloudCore's ISO/IEC 27001:2022 readiness assessment indicates that the organisation has established several foundational information security controls, but significant work remains before certification readiness. Of 59 assessed requirements and representative Annex A controls, 14 are fully implemented, 39 are partially implemented and 6 are not implemented. The portfolio readiness indicator is currently 56.8%. Priority gaps include ISMS internal audit, management review, independent information security review, privileged access management and vulnerability management. These areas require accelerated remediation because they represent significant governance or control-effectiveness weaknesses. Existing security practices provide a strong foundation for ISMS development; however, greater formalisation, evidence retention, governance and consistent control operation are required before CloudCore should proceed to certification assessment. |  |  |  |  | Implementation Status | Count | Remediation Metric | Count
[5 empty] | Implemented | 14 | Total Actions | 25
[5 empty] | Partially Implemented | 39 | Critical Priority | 5
[5 empty] | Not Implemented | 6 | High Priority | 20
[7 empty] | In Progress | 20
[7 empty] | Not Started | 5
25 | 5 | 20 | 5
Remediation Actions | Critical Priority | Actions In Progress | Actions Not Started
Certification Readiness Priorities
Internal Audit & Management Review: Establish and execute the formal ISMS internal audit programme and management review process before certification assessment. Independent Security Review: Complete an independent review of the organisation's information security approach and track resulting corrective actions. Privileged Access Management: Implement stronger privileged-access governance, including periodic recertification and time-limited administrative access. Vulnerability Management: Establish risk-based remediation SLAs and formal escalation requirements for overdue vulnerabilities. ISMS Governance & Evidence: Strengthen documentation, control ownership, evidence retention and traceability across the ISMS.
Certification Readiness Decision
NOT YET READY FOR CERTIFICATION ASSESSMENT
CloudCore should complete Critical remediation actions, establish the required ISMS governance activities and demonstrate consistent control operation before proceeding to an external certification audit.

## Methodology
CloudCore Systems Ltd — ISO/IEC 27001:2022 Gap Assessment Methodology
Assessment Status | Score | Definition | Assessment Metric | Result
Implemented | 1 | Requirement/control is implemented and supported by sufficient evidence. | Total Assessments | 59
Partially Implemented | 0.5 | Requirement/control is partly implemented but gaps or evidence deficiencies remain. | Total Readiness Score | 33.5
Not Implemented | 0 | Requirement/control is absent or materially ineffective. | Readiness % | 56.78%
Not Applicable | Excluded | Requirement/control is not applicable based on the organisation's context and documented justification.
Priority | Definition
Critical | Major certification-readiness issue requiring urgent remediation.
High | Significant gap requiring remediation before certification.
Medium | Control or process improvement required but lower immediate certification risk.
Low | Minor improvement, maintenance action or observation.
Assessment Approach
The assessment evaluates ISO/IEC 27001:2022 management system requirements and a representative risk-based selection of Annex A controls.
Implementation status is determined through review of documented processes, available evidence and identified control gaps.
Readiness scoring excludes controls formally assessed as Not Applicable.
The readiness percentage is an internal portfolio metric used to summarise assessment results and does not represent an official ISO certification score.
Certification readiness ultimately depends on conformity with applicable ISO/IEC 27001 requirements, effective implementation of the ISMS and successful independent certification audit.